## Slide 1: Project Monitoring and Control

## Slide 2: Project Monitoring and control
Monitoring : Collecting, Recording and Reporting information concerning project performance that project manager and other wish to know
Controlling: use data for monitor activity to bring actual performance to planned performance

## Slide 3: Project Monitoring and control
Why do we moinitor ?
What do we monitor?
When do we monitor?
How do we monitor?

## Slide 4: Why do we moinitor ?
Simply because we know that things don’t always go according to plan ( no matter how much we prepare)
To detect and react appropriately to deviations and change to plan

## Slide 5: What do we monitor?
Men (Human resource)
Machine
Money
Materials
Space
Time
Tasks
Quality/ Technical Performance

## Slide 6: What do we monitor?
Inputs | Outputs
Time | Progress
Money | Cost
Resources | Job starts
Material uses | Job completation
Tasks | Engineering/Design changes
Quality/Technical Performance | Variation order

## Slide 7: When do we monitor?
End of the project
Continously
Regularly
Logically
While there is still time to react
As soon as possible
At task completation
At pre planned decesion points( milestones)

## Slide 8: Where do we monitor?
At head office
At the site Office
On the spot
Depends on tha situation and 'whats'

## Slide 9: How do we monitor?
Through meetings with clients, parties involved in the project(contractors, suppliers etc)
For schedule-update CPA, PERT charts, update Gantt charts
Using earned value analysis
Calculate critical ratio
Milestones
Reports
Test and inspections
Delivery or staggered delivery
PMIS ( Project Management Information System)updating

## Slide 10: Meetings- Some monitoring issues
What problems do you have and what is being done to correct them?
What problems do you anticipate in the future?
Do you need any resources you do not yet have?
Do you need information you do not have yet?
Do you know anything that will give you schedule difficulties?
Any possibility your task will finish early/late?
Will your task be completed under/over/on budget?

## Slide 11: Project control cycle
Action
Correct deviation from plans
RE-PlAN as necessary
Plan
Specifications
Project schedule
Project budget
Resource plan
Vendor Contracts
Compare
Actual status against plan
Schedule
Cost
Monitor
Record status
Report progress
Report cost

## Slide 12: Project Control
Control- Process and activities needed to correct deviations from plan
Control the triple constraints
Time (Schedule)
Cost ( Budget, Expencess, etc)
Performance ( Specifications, Testing results, etc)

## Slide 13: Techniques for monitoring and contro(Earned value analysis and Critical ratio)
Earned value analysis
A way of measuring overall performance ( not individual task ) is using an aggregate performance meausre- Earned Value
Earned value of work performed (value completed) for those tasks in progress found my multiplying the estimated percent physical completion of work for each task by the planned costs for those tasks. The result is amount that should be spent on the task so far. This can be compared with actual spent.
Method for implementing percent completion(50-50 estimate, 0-100% rule, critical input rule, proportional rule, refered to earned value chart, earned value concept, baseline cost to completetion, actual cost to date)

## Slide 14: Earned value analysis - Variances
Four types of varainces
Cost(spending) variance(CV): difference between budgeted cost of work performed(earned value) (BCWP) and actual cost of the work performed (ACWP)
Schedule Variance(SV): difference between earned value and cost of work performed (BCWP) and cost of work we schedule to perform to date(BCWS)
Time variance (TV): difference between time schedule of the work perform (STWP) and actual time to perform it (ATWP)

## Slide 15: Earned value variance - formula
CV=BCWP-ACWP( Negative value- cost over run)
SV=BCWP-BCWS( Negative value- behind schedule)
TV=STWP-ATWP(Negative value-delay)
Index(Ratio)
Cost performance index(CPI)=BCWP/ACWP
Schedule performance Index(SPI)=BCWP/BCWS
Time performance Index(TPI)=STWP/ATWP

## Slide 16: Example
Assume that operations on work pacakge cost Rs 1500 to complete. They were scheduled originally finish today. At this point, we actually spent Rs 1350. And we estimate that we have completed two-third(2/3) of the work.What are the cost and schedule variance?
CV=BCWP-ACWP=1500(2/3)-1350= -350
SV= BCWP-BCWS=1500(2/3)-1500=-500
CPI=BCWP/ACWP= 1500(2/3)/1350=0.74
SPI=BCWP/BCWS= 1500(2/3)/1500=0.67
Spending higher than budget, and given what we have spent, we are not as far as along as we should be ( have not completed as much work as we should have)

## Slide 17
possible to have one of indicator to be favorable while other unfavorable
Might be ahead of schedule and behind cost

## Slide 18: Critical ratio
Sometimes, especially large projects it may be worthwhile calculating a set of critical ratio for all project activities
The critical ratio is
Actual progress Budgeted cost
Schedule progress Actual cost
If ratio is 1 everything is probably on target
The further away from 1 the ratio is, the more we may need to investigate

## Slide 19: Critical ratio example
Caculate the critical ratio for the following activities and indicate which are probably on target and need to be investigated
Activity | Actual progress | Schedule progress | Budgeted cost | Actual cost | Critical ratio(CR)
A | 4 days | 4 days | 60 | 40 | 
B | 3 days | 2 days | 50 | 50 | 
C | 2 days | 3 days | 30 | 20 | 
D | 1 days | 1 days | 20 | 30 | 
E | 2 days | 4 days | 25 | 25 | 

## Slide 20: Critical ratio example
Can be on schedule and below budget (Act A)
Why so good? Cutting corners?
Can be behind schedule but below budget( Act C)
Can be on budget but physical progress lagging( Act E)
Can be on schedule but cost running higher than budget ( Act D)
On budget ahead of schedule ( Act B)

## Slide 21: Summary
Need proper project monitoring and control mechanism
Tools available to help in monitoring and control activities
There are human control and management aspects not covered here